AI-POWERED PATIENT CARE SYSTEM

Proof of Concept / Minimum Viable Product

Technical Architecture Document & Implementation Guide

For Board of Directors Approval

| Document Version | 1.0 — Initial Release |
| --- | --- |
| Classification | Confidential |
| Prepared By | Chief Relations Officer |
| Target Audience | Board of Directors, IT Leadership, Clinical Leadership |
| POC Duration | 6 Weeks |
| Estimated POC Cost | USD 8,000 – 12,000 |

# 1. Executive Summary

This document presents the technical architecture and step-by-step implementation plan for a Proof of Concept (POC) / Minimum Viable Product (MVP) of an AI-powered patient care system. The POC is designed to demonstrate the core value proposition to the Board of Directors before committing to full-scale development.

The proposed system uses WhatsApp Business API as the patient communication channel, n8n as the automation and workflow engine, and Qwen 3.5 (qwen3.5:cloud) via Ollama Cloud API, and Jayasimma/healthcare model (local Ollama Docker) for clinical queries as the AI language model. The POC is intentionally scoped to four high-impact, demonstrable features that can be built, tested, and presented to the Board within six weeks.

POC Strategic Objective Demonstrate that AI-powered patient engagement via WhatsApp can measurably improve medicine adherence, reduce missed appointments, and provide a safety net through emergency response — using a lean, low-cost technology stack that can scale to the full system upon Board approval.

## What the POC Will Prove

| Hypothesis | How It Is Demonstrated | Success Threshold |
| --- | --- | --- |
| AI can remind patients and track adherence via WhatsApp | Live medicine reminders sent and confirmed by 10 test patients over 2 weeks | ≥ 80% confirmation rate |
| AI chatbot can handle patient symptom queries safely | Simulated symptom conversations reviewed by clinical team | 0 unsafe responses in review |
| Next-of-kin can be kept informed automatically | Daily summaries sent to family contacts of test patients | Family satisfaction score ≥ 4/5 |
| SOS emergency alert reaches the right person | Live SOS trigger tested end-to-end with emergency desk | Response time ≤ 3 minutes |

# 2. POC Scope Definition

The POC deliberately excludes complex integrations to enable rapid delivery. The scope boundary is drawn to maximise demonstrability with minimum technical risk.

## 2.1 Features Included in POC

| # | Feature | Why Included |
| --- | --- | --- |
| 1 | Patient Onboarding via WhatsApp | First interaction — establishes daily routine, collects consent |
| 2 | Medicine Reminder & Adherence Tracking | Highest clinical value, most tangible to demonstrate |
| 3 | AI Symptom Chatbot (Qwen 3.5 + Jayasimma/Healthcare) | Showcases AI capability — most compelling for Board |
| 4 | Daily Summary to Next-of-Kin | Demonstrates family engagement — strong emotional impact |
| 5 | SOS Emergency Alert | Non-negotiable safety feature — critical for approval |
| 6 | Care Team WhatsApp Notification | Closes the clinical loop — shows system-wide connectivity |

## 2.2 Features Deferred to Full System

| Feature | Reason for Deferral | Full System Phase |
| --- | --- | --- |
| Wearable Device Integration | Requires OAuth portal development + DPA with Apple/Fitbit | Phase 3 |
| AI Deterioration Prediction Engine | Requires 90 days of adherence data to train/validate | Phase 5 |
| Voice Note Support (Whisper STT) | Adds complexity without changing core demo value | Phase 4 |
| Family Group Broadcast | WhatsApp group management adds overhead; individual next-of-kin sufficient for POC | Phase 6 |
| Hospital HIS Integration | HIS API mapping takes 4–6 weeks; PostgreSQL used as mock DB for POC | Phase 2 |
| Appointment Management | Requires calendar system access; manual entry sufficient for POC | Full system |
| Exercise Monitoring | Dependent on wearable integration | Phase 3 |
| Multilingual Voice Reply (TTS) | Arabic TTS nice-to-have; not core to clinical demonstration | Phase 4 |

# 3. POC Technical Architecture

## 3.1 Architecture Overview

The POC uses a deliberately simplified, three-layer architecture. Clinical AI inference runs locally in Docker (Jayasimma/healthcare model); general AI and workflow orchestration uses Ollama Cloud API (Qwen 3.5). No on-premise servers beyond a single Docker host are required. This minimises setup time and infrastructure cost while delivering a fully functional demonstration.

Architecture Principle For the POC, speed of delivery and demonstrability take priority over production-grade resilience. The architecture is designed so that every component can be upgraded or replaced without changing the overall data flow when moving to the full system.

## 3.2 System Layers

| Layer | Component | Role | Hosting |
| --- | --- | --- | --- |
| Data Layer | PostgreSQL | Mock hospital database — patient profiles, medicine schedules, next-of-kin contacts | Docker container (local) |
| Orchestration Layer | n8n (Docker) | Workflow automation, scheduling, LLM routing, WhatsApp message dispatch | Docker container (self-hosted) |
| Intelligence Layer | Qwen 3.5 (Ollama Cloud API) + Jayasimma/Healthcare (Local Ollama Docker) | AI conversation, symptom triage, reminder personalisation, escalation logic | Ollama Cloud API (Qwen 3.5) / Local Docker (Jayasimma/Healthcare) |
| Communication Layer | WhatsApp via Twilio | Patient-facing messaging, media, quick-reply buttons, SOS trigger | Twilio Cloud |
| Notification Layer | WhatsApp Group / Email | Care team alerts, next-of-kin daily summaries, emergency desk SOS | WhatsApp / Twilio |

## 3.3 Docker Compose Stack

The entire POC back-end is defined in a single docker-compose.yml file. Running docker compose up -d starts three containers that communicate over an internal Docker network (poc-network). The reference configuration is shown below.

version: "3.9"

services:

postgres:

image: postgres:16

environment:

POSTGRES_DB: poc_db

POSTGRES_USER: poc_user

POSTGRES_PASSWORD: ${POSTGRES_PASSWORD}

volumes: [postgres_data:/var/lib/postgresql/data]

networks: [poc-network]

ollama:

image: ollama/ollama

ports: ["11434:11434"]

volumes: [ollama_data:/root/.ollama]

networks: [poc-network]

n8n:

image: n8nio/n8n

ports: ["5678:5678"]

depends_on: [postgres, ollama]

environment:

DB_TYPE: postgresdb

DB_POSTGRESDB_HOST: postgres

DB_POSTGRESDB_DATABASE: poc_db

DB_POSTGRESDB_USER: poc_user

DB_POSTGRESDB_PASSWORD: ${POSTGRES_PASSWORD}

OLLAMA_API_KEY: ${OLLAMA_API_KEY}   # Qwen 3.5 Cloud

OLLAMA_HC_URL: http://ollama:11434   # Jayasimma/healthcare

volumes: [n8n_data:/home/node/.n8n]

networks: [poc-network]

networks:

poc-network:

volumes:

postgres_data: {}  ollama_data: {}  n8n_data: {}

After starting the stack, pull the local healthcare model: docker exec -it ollama ollama pull Jayasimma/healthcare. Qwen 3.5 (qwen3.5:cloud) is accessed via Ollama Cloud API using the OLLAMA_API_KEY credential — no local pull needed. Ensure the host machine has at least 8 GB RAM and 10 GB free disk space for the Jayasimma/healthcare model.

3.4 POC Data Flow

The following describes the end-to-end data flow for the two most critical POC scenarios.

### Scenario A — Medicine Reminder & Adherence Confirmation

| Step | Action | Component |
| --- | --- | --- |
| 1 | Daily schedule pulled from PostgreSQL at 11:00 PM | n8n scheduled workflow |
| 2 | Patient medicine timings calculated relative to stored routine | n8n Code node |
| 3 | Reminder message generated by Qwen 3.5 via Ollama Cloud API (warm, personalised tone) | Ollama Cloud API (Qwen 3.5) / Local Docker (Jayasimma/Healthcare) |
| 4 | WhatsApp message with quick-reply buttons sent to patient | Twilio WhatsApp API |
| 5 | Patient taps 'Taken' or 'Skipped' on their phone | WhatsApp webhook → Twilio |
| 6 | Response captured by n8n webhook; adherence record updated in Sheets | n8n + PostgreSQL |
| 7 | End-of-day summary compiled and sent to next-of-kin | n8n + Twilio |

### Scenario B — Patient Symptom Query via Chatbot

| Step | Action | Component |
| --- | --- | --- |
| 1 | Patient sends free-text symptom message via WhatsApp | Twilio webhook → n8n |
| 2 | Message type classified (symptom / general / SOS keyword) | n8n Switch node |
| 3 | Patient context (age, conditions, medicines) retrieved from Sheets | n8n + PostgreSQL |
| 4 | Symptom payload routed to Jayasimma/healthcare (Local Docker); general queries to Qwen 3.5 (Ollama Cloud) | Ollama Cloud API (Qwen 3.5) / Local Docker (Jayasimma/Healthcare) |
| 5 | AI response generated; red-flag keywords checked against predefined list | n8n Code node |
| 6 | If red-flag: escalate to care team WhatsApp + log. If safe: reply to patient | n8n Switch + Twilio |
| 7 | Full conversation thread appended to patient record in PostgreSQL | n8n + PostgreSQL |

# 4. Technology Stack

## 4.1 Component Details

| Component | Product | Version / Tier | Cost (POC) | Why Chosen |
| --- | --- | --- | --- | --- |
| Workflow Engine | n8n (Docker) | Starter plan | USD 0 | Docker self-hosted, visual workflow builder, WhatsApp + HTTP native nodes, unlimited executions |
| AI Language Model | Qwen 3.5 (Ollama Cloud API) + Jayasimma/Healthcare (Local Ollama Docker) | Ollama Cloud API (Qwen 3.5) / Local Docker (Healthcare model) | ~USD 150–250 (6 weeks) | Qwen 3.5 via Ollama Cloud for general tasks (Arabic quality, low latency); Jayasimma/healthcare local Docker for medical symptom triage (domain-trained, data stays on-premise) |
| Messaging | Twilio WhatsApp Business API | Pay-per-message | ~USD 50–80 (6 weeks) | Fastest BSP setup, n8n native integration, robust sandbox for testing |
| Mock Database | PostgreSQL | Free tier | Free | Zero setup time, easy manual data entry, n8n native PostgreSQL node |
| Care Team Alerts | WhatsApp Group + Email | Existing | Free | No additional integration needed; uses existing hospital WhatsApp |
| Code Repository | GitHub (private repo) | Free | Free | Version control for all n8n workflow exports and configuration files |
| Documentation | Google Docs / this document | Free | Free | Accessible to all stakeholders |

## 4.2 API Credentials Required

| Credential | Where Obtained | Time to Obtain | Stored In |
| --- | --- | --- | --- |
| OLLAMA_API_KEY | ollama.com → Account → API Keys → Generate New Key | Immediate | n8n Credential Vault |
| TWILIO_ACCOUNT_SID | console.twilio.com → Account Info | Immediate after registration | n8n Credential Vault |
| TWILIO_AUTH_TOKEN | console.twilio.com → Account Info | Immediate after registration | n8n Credential Vault |
| TWILIO_WHATSAPP_NUMBER | Twilio WhatsApp Sandbox (testing) → Verified number (production) | Sandbox: immediate; Production: 7–14 days | n8n Credential Vault |
| POSTGRES_PASSWORD | n8n PostgreSQL node using Docker Compose .env values | 30 minutes | n8n PostgreSQL credential |
| WHATSAPP_WEBHOOK_SECRET | Generated by n8n when setting up Twilio webhook | 5 minutes | n8n + Twilio dashboard |

# 5. Security & Compliance (POC)

Important Note for the Board The POC will use synthetic (fake) patient data and willing staff volunteers. No real patient identifiable data will be transmitted to any cloud service until the full Data Processing Agreements are signed and reviewed by the hospital's legal team. This is a firm boundary.

| Area | POC Approach | Full System Upgrade |
| --- | --- | --- |
| Patient Data | Synthetic data only; staff volunteers use their own consent forms | Full PDPL-compliant patient consent workflow |
| API Key Management | All keys stored in n8n Credential Vault; never in code or Sheets | Same — vault is production-grade |
| Data Anonymisation | Patient names replaced with hash IDs before any Ollama API call | Same — middleware node in every workflow |
| Data at Rest | PostgreSQL running in Docker container with volume persistence (locally controlled) | Hospital HIS with role-based access control |
| Transmission Security | All API calls over HTTPS / TLS 1.3 | Same |
| Access Control | n8n Docker container with admin account restricted to IT team only | Same Docker n8n with LDAP/SSO integration |
| Audit Logging | n8n execution history retained for 30 days | Dedicated audit log database with 7-year retention |
| DPA Status | Ollama runs locally in Docker — no cloud DPA required; Twilio DPA in place | Full vendor DPA portfolio for all cloud services |

# 6. Infrastructure Requirements

## 6.1 POC Infrastructure — What Is Needed

| Item | Specification | Who Provides | Cost |
| --- | --- | --- | --- |
| n8n (Docker) account | Self-hosted Docker container — unlimited workflow executions | Included in docker-compose.yml — docker compose up -d | USD 0 |
| Ollama Cloud (Qwen 3.5) + Local Ollama Docker (Healthcare) | Docker container (ollama/ollama) for Jayasimma/healthcare; Ollama Cloud API key for Qwen 3.5 | Included in Docker Compose stack — no external registration | USD 150–250 for 6 weeks (Qwen Cloud tokens only) |
| Twilio account | WhatsApp sandbox for testing; production number for live demo | IT team registers at twilio.com | USD 50–80 for 6 weeks |
| PostgreSQL Database | Hospital already has this | Existing hospital account | Free (existing) |
| Test phone numbers | 10 staff volunteer phones for POC testing | IT team coordinates with HR | Free |
| WhatsApp Business number | One dedicated hospital phone number for the system | Procurement of a SIM card | ~USD 20 one-time |
| Total POC Infrastructure |  |  | USD 8,000–12,000 (incl. labour) |

Docker-Based Deployment — All Services in Containers The entire POC runs as a Docker Compose stack on a single hospital server (or local machine for development). Three containers are deployed: n8n (workflow engine), PostgreSQL (database), and Ollama (local LLM inference). No cloud AI or cloud database services are required. The only external services are Twilio (WhatsApp messaging) and GitHub (code repository). The only physical item required is one dedicated SIM card for the hospital WhatsApp Business number.

# 7. Step-by-Step Development Guide

The following guide is structured into six weeks. Each week has a clear deliverable. The total estimated effort is 200–240 person-hours for a team of two (one IT developer and one clinical coordinator).

## WEEK 1 — Accounts, Setup & Data Preparation

Deliverable: All credentials active, test data in PostgreSQL, n8n connected to all services.

| 1.1 | Register and configure n8n (Docker) • Create a docker-compose.yml file on the hospital server with services: n8n, PostgreSQL, and Ollama. • Use the official n8n Docker image (n8nio/n8n) — no execution limits. • Install the following built-in nodes: PostgreSQL, HTTP Request, WhatsApp Business (Twilio), Schedule Trigger, Webhook, IF, Switch, Code. • Enable n8n's built-in credential encryption — verify it is on in Settings → Security. • Access n8n at http://localhost:5678 and complete the initial admin user setup. Share the URL with the development team only. |
| --- | --- |

| 1.2 | Set up Ollama (Docker + Cloud) and configure both LLMs • Ollama is already running as part of the Docker Compose stack from Step 1.1 (for the local healthcare model). • Pull the healthcare model into the Ollama container: docker exec -it ollama ollama pull Jayasimma/healthcare • Verify the model is loaded: docker exec -it ollama ollama list — confirm Jayasimma/healthcare appears. • For Qwen 3.5 Cloud: test with: curl -H 'Authorization: Bearer [KEY]' https://api.ollama.com/v1/chat/completions -d '{"model":"qwen3.5:cloud","messages":[{"role":"user","content":"Hello"}]}' • Test Healthcare model (local): curl http://localhost:11434/api/chat -d '{"model":"qwen3.5:cloud","messages":[{"role":"user","content":"Hello"}]}' — confirm a JSON response is returned. • In n8n, add two credentials: (1) Ollama-Healthcare: HTTP Request, Base URL http://ollama:11434, no auth. (2) Ollama-Qwen: HTTP Header Auth, header Authorization: Bearer [OLLAMA_API_KEY], Base URL https://api.ollama.com. |
| --- | --- |

| 1.3 | Register Twilio and set up WhatsApp sandbox • Go to twilio.com, create a free account, and verify with the hospital phone number. • Navigate to Messaging → Try WhatsApp → WhatsApp Sandbox. • Note the sandbox number and the join code (e.g., 'join silver-fox'). • All 10 test volunteers must send the join code from their personal WhatsApp to activate the sandbox. • Record TWILIO_ACCOUNT_SID and TWILIO_AUTH_TOKEN from Console → Account Info. • Store both in n8n Credential Vault. • For the live demo, submit a WhatsApp Business profile approval request in parallel — this runs concurrently and takes 7–14 days. |
| --- | --- |

| 1.4 | Initialise the PostgreSQL mock database • PostgreSQL is already running as part of the Docker Compose stack. • Create four tables: patients, medicines, schedule, adherence_log using the SQL init script in the repository. • patients table columns: patient_id (PK), first_name, last_name, age, gender, phone, next_of_kin_name, next_of_kin_phone, wake_time, breakfast_time, lunch_time, dinner_time, bed_time, consent_given. • medicines table columns: medicine_id (PK), patient_id (FK), medicine_name, dose, frequency, timing_instruction, duration_days, start_date. • schedule table: auto-populated by n8n from the above two tables — do not edit manually. • adherence_log table columns: log_id (PK), patient_id (FK), log_date, medicine_name, scheduled_time, actual_response, response_time, status. • Seed 10 synthetic test patients using the provided SQL seed script (all fictional — no real patient data). • Share the sheet with the Google account linked to n8n's Google credential. |
| --- | --- |

| 1.5 | Connect all credentials in n8n and verify • In n8n, go to Credentials and add: Ollama-Qwen (HTTP Header Auth with OLLAMA_API_KEY), Ollama-Healthcare (HTTP Request to local), Twilio (Account SID + Auth Token), PostgreSQL (host=postgres, port=5432, database=poc_db, user=poc_user, password from .env). • Build a simple 3-node test workflow: Schedule Trigger → PostgreSQL Query (SELECT * FROM patients LIMIT 1) → HTTP Request to Jayasimma/healthcare (http://ollama:11434/api/chat). Run it manually and confirm all three nodes execute without errors. • Build a second test: Webhook → Twilio Send WhatsApp → confirm a WhatsApp message arrives on a test phone. • Screenshot all passing tests — these become evidence for the Board presentation. • Duration estimate for Week 1: 40–50 hours. |
| --- | --- |

## WEEK 2 — Patient Onboarding & Routine Collection

Deliverable: A patient can be enrolled via WhatsApp and their daily routine stored in PostgreSQL.

| 2.1 | Build the onboarding conversation flow • Create an n8n workflow triggered by a new WhatsApp message containing the keyword 'START' or the patient's enrolled phone number appearing for the first time. • Step 1 of conversation: Send a welcome message — 'Hello [Name], I am your personal health assistant from [Hospital Name]. I will help you manage your medicines and health schedule. May I have your permission to send you daily health updates? Reply YES to continue.' • Capture YES/NO response. If NO, log and stop. If YES, mark ConsentGiven = TRUE in PostgreSQL. • Step 2: Ask for wake-up time — 'Thank you! To personalise your reminders, please tell me: what time do you usually wake up? (e.g., 7:00 AM)' • Capture and validate time format. If invalid, re-ask with an example. • Repeat for: breakfast time, lunch time, dinner time, bedtime. • Store all five times in the Patients tab for that patient's row. • Send confirmation: 'Perfect! I have saved your schedule. Your medicine reminders will be timed around your day. You can update your schedule anytime by sending UPDATE.' |
| --- | --- |

| 2.2 | Build the schedule computation node • Create an n8n Code node that runs after routine collection and computes exact reminder times for each medicine. • Logic: if timing instruction is 'before breakfast', reminder = breakfast time minus 30 minutes; if 'after breakfast', reminder = breakfast time plus 30 minutes; if 'with lunch', reminder = lunch time; if 'before bed', reminder = bedtime minus 20 minutes; if 'morning empty stomach', reminder = wake time plus 15 minutes. • Write computed times into the Schedule tab in PostgreSQL (one row per medicine per patient per day). • Test with all five timing instruction variants. Verify computed times are correct for three synthetic patients. |
| --- | --- |

| 2.3 | Implement the UPDATE routine command • Build a parallel workflow triggered when a patient sends the word 'UPDATE'. • Re-run the routine collection conversation (same five questions). • Overwrite the stored times in PostgreSQL. • Recompute all medicine reminder times. • Confirm to patient: 'Your schedule has been updated successfully.' • Test: enrol a patient, update their breakfast time, verify the medicine reminders shift accordingly. |
| --- | --- |

## WEEK 3 — Medicine Reminder Engine & Adherence Tracking

Deliverable: Reminders fire at the right times, patients can confirm/skip, adherence is logged.

| 3.1 | Build the daily schedule loader • Create an n8n workflow on a Schedule Trigger at 11:00 PM every night. • Read all rows from the Schedule tab in PostgreSQL for the following day. • For each row, create a scheduled n8n trigger (using the n8n Schedule node or HTTP API to create future workflow executions) at the computed reminder time. • Each scheduled execution carries: PatientID, Phone, MedicineName, Dose, TimingInstruction, ScheduledTime. |
| --- | --- |

| 3.2 | Build the reminder message generator • When a scheduled trigger fires, call the Qwen 3.5 Ollama Cloud API (for reminder generation) with the following system prompt: • 'You are a warm, caring health assistant. Generate a short, friendly WhatsApp reminder (max 60 words) for a patient to take their medicine. Patient is [Age], taking [MedicineName] [Dose] [TimingInstruction]. Use a warm tone, like a family member reminding. Include the medicine name. End with two reply options: 1-Taken, 2-Not yet. Do not use clinical language.' • Append quick-reply buttons in the Twilio API call: button 1 = '✅ Taken', button 2 = '⏰ Remind me in 30 min', button 3 = '❌ Skipped today'. • Send the WhatsApp message using the Twilio node. |
| --- | --- |

| 3.3 | Build adherence response capture • Create a Twilio webhook workflow in n8n that fires on every incoming WhatsApp message. • At the entry point, check if the incoming message matches a pending reminder (match by PatientID + time window of 2 hours). • If match: parse the response (Taken / Remind / Skipped). Log to AdherenceLog tab with timestamp and status. • If 'Remind me in 30 min': re-schedule the same reminder using a 30-minute delay in n8n. • If no response after 2 hours: log as 'No Response' and flag for daily summary. • Send confirmation reply to patient: '✅ Noted! [MedicineName] marked as taken at [time].' or appropriate variant. |
| --- | --- |

| 3.4 | Build the daily adherence summary for next-of-kin • Create a 9:00 PM daily workflow that reads the AdherenceLog for the current day. • For each patient, compute: total reminders sent, total taken, total skipped, total no-response. • Call Ollama API to generate a warm family-update message (max 100 words) summarising the day. • System prompt: 'You are writing a daily health update to the family of [Patient Name]. Write warmly and factually. Medicines taken: [list]. Medicines missed: [list]. Overall today: [good/needs attention]. Do not alarm unnecessarily. Keep under 100 words.' • Send message to NextOfKinPhone via Twilio. • Log the send in PostgreSQL. |
| --- | --- |

## WEEK 4 — Symptom Chatbot, SOS & Care Team Alerts

Deliverable: Patient can describe symptoms, AI responds safely, SOS triggers emergency alert.

| 4.1 | Build the incoming message classifier • At the top of the Twilio webhook workflow, add a Switch node that classifies every incoming message into one of four categories: • Category A — Adherence response: message matches a pending reminder (handled by Week 3 flow). • Category B — SOS: message contains keywords 'SOS', 'emergency', 'help', 'مساعدة', 'طوارئ' (Arabic equivalents). • Category C — Symptom / health query: message contains health-related keywords or is a free-text message not matching A or B. • Category D — Other: greetings, update requests, general questions (route to Qwen for general response). • Use a combination of keyword matching and a short Qwen classification call to categorise ambiguous messages. |
| --- | --- |

| 4.2 | Build the symptom chatbot flow • For Category C messages, retrieve the patient's profile from PostgreSQL (age, conditions, current medicines). • Route symptom messages to the Jayasimma/healthcare model (local Docker, http://ollama:11434/api/chat). Build the API call with this system prompt: 'You are a compassionate AI health assistant for [Hospital Name]. A patient has sent you a health concern. Your role is to listen, ask one clarifying question if needed, and provide general supportive guidance. Never diagnose. Never recommend stopping medicines. If symptoms are serious (chest pain, difficulty breathing, sudden weakness, severe headache, vision changes), immediately advise the patient to call emergency services and flag this conversation. Patient profile: [age], [conditions], [medicines]. Respond in the patient's language (Arabic or English). Keep responses under 150 words.' • Check the AI response for the predefined escalation phrases ('call emergency', 'seek immediate care', 'go to hospital'). • If escalation phrase is present: trigger the care team alert flow (Step 4.3). • Append the full conversation to a ConversationLog sheet in PostgreSQL. |
| --- | --- |

| 4.3 | Build the care team alert workflow • When an escalation is triggered (by symptom chatbot or SOS), compile a structured alert message. • Alert format: '🔴 PATIENT ALERT — [Name] ¦ [Age] ¦ [Phone] ¦ [Time]. Symptom reported: [patient message]. AI assessment: [AI response excerpt]. Conversation log: [link to PostgreSQL row]. Please contact patient immediately.' • Send this alert to the designated care team WhatsApp number (or group) via Twilio. • Also send an email via n8n's built-in Email node to the duty physician's hospital email. • Log the escalation in a separate Escalations tab in PostgreSQL with timestamp and outcome field (to be filled manually by care team). • Notify the patient: 'I have shared your concern with our care team. A doctor will be in touch with you shortly. If this is an emergency, please call [hospital emergency number] immediately.' |
| --- | --- |

| 4.4 | Build the SOS emergency alert flow • For Category B SOS messages, execute an immediate high-priority flow (bypasses all other processing). • Simultaneously: (a) Send SOS alert to the emergency department WhatsApp with patient name, phone, and location if available. (b) Send alert to next-of-kin. (c) Send acknowledgement to patient. • Patient acknowledgement: '🆘 EMERGENCY ALERT SENT. Our emergency team has been notified and will contact you immediately. If you can, please stay on your phone. If you are in immediate danger, call [112 / emergency number] now.' • Log the SOS event with a timestamp in the Escalations tab. • Test this flow five times with different staff volunteers before the live demo — response time must be under 3 minutes. |
| --- | --- |

## WEEK 5 — End-to-End Testing & Refinement

Deliverable: All four features working reliably across 10 test patients for 5 consecutive days.

| 5.1 | Internal QA testing • Run the complete system with synthetic data for 2 days before involving human volunteers. • Verify: all 10 patient profiles receive the correct number of reminders at the correct times, all adherence responses are logged correctly, Ollama API calls return valid responses within 8 seconds, SOS alert reaches the designated phone within 90 seconds, next-of-kin summary arrives at 9:00 PM. |
| --- | --- |

| 5.2 | Staff volunteer pilot (5 days) • Enrol 10 consenting staff members. Use their real WhatsApp numbers. Enter fictional (but plausible) medicine schedules for each. • Run the full system for five working days. Collect daily feedback from each volunteer via a 3-question WhatsApp survey: (1) Did you receive all your reminders on time? (2) Was the chatbot response helpful when you asked a health question? (3) Rate your overall experience 1–5. • Document every bug, failed message, or incorrect response. • Clinical coordinator reviews every chatbot response for safety and appropriateness. |
| --- | --- |

| 5.3 | Arabic language testing • Have at least 3 of the 10 volunteers interact entirely in Arabic. • Test Qwen 3.5’s Arabic response quality (Ollama Cloud) and Jayasimma/healthcare’s clinical accuracy (Local Docker): send 10 representative patient messages in Arabic (medicine questions, symptom descriptions, greeting variations). • Have an Arabic-speaking clinical staff member rate each response for: language quality, clinical safety, tone appropriateness. • Target: all 10 Arabic responses rated 4+ out of 5 on all three dimensions. • If any dimension scores below 4, refine the Qwen system prompt and retest. |
| --- | --- |

| 5.4 | Performance & cost baseline • Record the following metrics over the 5-day pilot: average Ollama API response time, total API calls made, total Twilio messages sent, n8n workflow execution success rate, total cost incurred across all services. • Compare actual cost to the estimate in Section 6. Document any variance. • Test n8n workflow behaviour when Ollama API returns an error — verify the fallback message is sent to the patient rather than silence. • Produce a one-page performance summary for the Board presentation. |
| --- | --- |

## WEEK 6 — Demo Preparation & Board Presentation

Deliverable: Board-ready live demonstration and a formal approval recommendation document.

| 6.1 | Prepare the live demonstration script • The Board demonstration should be live (not a recording) to maximise credibility. • Demonstration Scenario 1 — Medicine Reminder: Trigger a live reminder on a designated volunteer's phone. The Board watches the message arrive, the volunteer taps 'Taken', and the confirmation is logged in real time on the projected Google Sheet. • Demonstration Scenario 2 — Symptom Chatbot: A Board member sends a pre-scripted symptom message to the system and watches the AI respond in Arabic and English within seconds. • Demonstration Scenario 3 — SOS Alert: Trigger an SOS from a test phone. Board watches the emergency alert arrive on the projected care team WhatsApp simultaneously. • Demonstration Scenario 4 — Next-of-Kin Summary: Show a pre-generated daily summary sent to a next-of-kin's phone. |
| --- | --- |

| 6.2 | Compile the POC results report • Produce a one-page quantitative results summary: total patients enrolled, total reminders sent, overall adherence rate, total chatbot conversations, escalation count, SOS tests passed, API uptime, cost actual vs estimate. • Include 3–5 anonymised screenshots of WhatsApp conversations (Arabic and English). • Include verbatim volunteer feedback quotes (with permission). • Include one quote from the clinical coordinator reviewing chatbot safety. • Frame everything as: 'Here is what the POC proved. Here is what the full system will deliver. Here is what we are asking the Board to approve.' |
| --- | --- |

| 6.3 | Full system roadmap and investment ask • Present the phased full system plan (Phases 1–8 from this document) with timeline and budget. • Clearly state the three decisions the Board needs to make: (1) Approve full system development budget, (2) Approve dedicated IT team resources, (3) Approve legal team to execute DPAs with Ollama, Apple, Fitbit, and WhatsApp BSP. • Show the total cost of full system vs estimated cost savings (reduced readmission rates, reduced call centre load, reduced missed appointments). • Provide a conservative ROI calculation: if the system reduces hospital readmissions by just 5% in the target patient cohort, what is the financial impact? |
| --- | --- |

# 8. POC Success Metrics & KPIs

| Metric | Target | How Measured | Failure Threshold |
| --- | --- | --- | --- |
| Medicine adherence confirmation rate | ≥ 80% of reminders receive a response | AdherenceLog tab — % rows with status ≠ No Response | < 65% |
| Reminder delivery success rate | ≥ 98% of scheduled messages delivered | Twilio delivery receipts in n8n logs | < 95% |
| AI chatbot response time | ≤ 8 seconds | n8n execution time log on Ollama HTTP node | > 15 seconds avg |
| AI response clinical safety | 0 unsafe responses in 50 test interactions | Clinical coordinator manual review | Any unsafe response |
| Arabic language quality score | ≥ 4.0 / 5.0 | Staff volunteer ratings across 10 Arabic conversations | < 3.5 average |
| SOS alert delivery time | ≤ 3 minutes end-to-end | Timestamp in Escalations tab vs SOS send time | > 5 minutes |
| Volunteer satisfaction score | ≥ 4.0 / 5.0 overall experience | 5-day pilot daily survey average | < 3.5 |
| System uptime | ≥ 99% during pilot period | n8n workflow success rate | < 95% |
| POC total cost | ≤ USD 12,000 | Sum of all invoices across 6 weeks | > USD 15,000 |

# 9. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| WhatsApp Business API approval delayed (> 14 days) | Medium | High | Use Twilio sandbox for testing throughout; production approval runs in parallel from Day 1 |
| Ollama Cloud API rate limits (Qwen 3.5) or healthcare model slowness during demo | Low | High | Implement retry logic in n8n; pre-warm the Jayasimma/healthcare container; request higher rate limits from Ollama Cloud for Qwen 3.5 before demo week |
| Qwen Arabic responses below quality threshold | Low | Medium | System prompt refinement; have Arabic-speaking clinical reviewer from Week 3 onwards |
| PostgreSQL concurrent edit conflicts | Low | Low | PostgreSQL handles concurrent writes with row-level locking; no conflict issues at POC scale |
| n8n (Docker) execution limit exceeded (5,000/month) | Low | Medium | Monitor execution count weekly; scale Docker resources (CPU/RAM) on the host server |
| Staff volunteer dropout from pilot | Medium | Low | Enrol 12 volunteers instead of 10 as buffer; keep participation commitment under 5 min/day |
| Ollama Docker container failure during Board demo | Very Low | Critical | Restart the Ollama Docker container; pre-record a 2-minute backup video as contingency; verify GPU/CPU allocation before demo day |

# 10. POC Budget Estimate

| Item | Unit | Qty | Unit Cost (USD) | Total (USD) |
| --- | --- | --- | --- | --- |
| n8n (Docker) — self-hosted | Month | 2 | 20 | 40 |
| Ollama Cloud — Qwen 3.5 tokens (general AI tasks) | Cloud tokens (Qwen 3.5) | 1 | 200 | 200 |
| Twilio WhatsApp messages (test + demo) | Messages | 5,000 | 0.005 | 25 |
| Twilio WhatsApp phone number | Month | 2 | 1 | 2 |
| WhatsApp Business profile verification fee | One-time | 1 | 0 | 0 |
| Dedicated SIM card for WhatsApp number | One-time | 1 | 20 | 20 |
| Developer time (1 developer × 6 weeks × 40 hrs) | Hours | 240 | 30 | 7,200 |
| Clinical coordinator time (20% × 6 weeks) | Hours | 48 | 50 | 2,400 |
| Contingency (10%) |  |  |  | 1,000 |
| TOTAL POC INVESTMENT |  |  |  | ~10,887 |

Full System Investment Context The POC investment of approximately USD 11,000 represents less than 2% of the estimated full system development cost (USD 600,000–800,000 over 18 months). A successful POC provides the evidence base to justify the full investment to the Board with confidence.

# 11. From POC to Full System

## 11.1 What Carries Forward Unchanged

| POC Component | Status in Full System |
| --- | --- |
| n8n workflow engine | Upgraded to production Docker n8n Enterprise; all POC workflows migrate without rewriting |
| Dual-LLM stack carried forward: Qwen 3.5 (Ollama Cloud) + Jayasimma/healthcare (Local Docker); add additional models as needed via ollama pull | Same Docker setup; pull additional models as needed (Llama 3.3, BioMistral, Whisper) via ollama pull |
| WhatsApp via Twilio | Same integration; phone number graduates to verified business account |
| Qwen 3.5 and Jayasimma/healthcare system prompts | Refined versions used as-is in the full system |
| PostgreSQL data schema | Migrated to hospital HIS; table schema becomes the API field mapping reference |
| Onboarding conversation flow | Extended with wearable enrolment and family group setup; core questions unchanged |

## 11.2 What Gets Added After Board Approval

| Phase | Feature | Timeline After Approval |
| --- | --- | --- |
| Phase 2 | Hospital HIS integration (replace PostgreSQL mock DB) | Weeks 1–5 |
| Phase 3 | Wearable Device APIs (Apple HealthKit + Fitbit) | Weeks 4–7 |
| Phase 4 | Voice note support (Whisper STT + Arabic TTS) | Weeks 5–7 |
| Phase 5 | AI Deterioration Prediction Engine (30-day risk score) | Weeks 7–11 |
| Phase 6 | Family Group Broadcast (WhatsApp Groups) | Weeks 8–10 |
| Phase 7 | Care Team Dashboard (real-time web portal) | Weeks 9–13 |
| Phase 8 | On-premise n8n + LLM migration (when patient volume warrants) | Weeks 14–18 |

# 12. Recommendation to Board

Recommendation Approve the POC budget of USD 11,000 and a 6-week timeline. Assign one IT developer and one clinical coordinator as dedicated resources. The POC will produce a live, functioning demonstration that directly informs the Board's decision on the full system investment. If the POC meets all success metrics defined in Section 8, the Chief Relations Officer recommends proceeding immediately to Phase 1 of the full system.

| Board Decision Required | Details |
| --- | --- |
| Approve POC budget: USD 11,000 | Covers 6-week development, cloud services, and staff time |
| Assign IT developer (100% for 6 weeks) | One mid-senior developer with API integration experience |
| Assign clinical coordinator (20% for 6 weeks) | Reviews AI responses, coordinates volunteer pilot, validates metrics |
| Authorise legal team to initiate Ollama DPA review | Signing the DPA is a prerequisite for handling any real patient data — can begin immediately with synthetic data POC |
| Set Board presentation date (Week 6) | Reserve a 45-minute slot for the live demonstration and results review |

End of Document